Facilité de Coopération Technique (FCT) – Maroc  
Décision n° NDICI-GEO-NEAR/2022/ACT-61040

Jumelage léger

Renforcement des capacités de la Cour des comptes du Royaume du Maroc en certification des comptes de l’état, en évaluation des programmes et projets publics et en appréciation de l’exécution budgétaire.

MA 22 NDICI FI 01 25 TWL

Calendrier de lancement et de mise en œuvre (INDICATIF)

| Action délai | Mois | Date |
| --- | --- | --- |
| Finalisation fiche : | 0 | Juillet 2025 |
| Lancement de l’appel à propositions: | M+1 | Jeudi 28/8/2025 |
| minimum 8 semaines |  |  |
| Information day + vc |  |  |
| Q&A à publier le cas échéant |  | Avant le jeudi 23/10/2025 |
| Réception des propositions : | M+3 | Lundi 10/11/2025 |
| Réunions de sélection : |  | Vendredi 14 novembre 2025 |
| idéalement 2 semaines exceptionnellement jusque 4 semaines |  |  |
| Notification des Etats membres : | m+4 | Lundi 24 novembre 2025 |
| 1 semaine maxi |  |  |
| Confirmation Etat membre sélectionné : |  | Lundi 1 décembre 2025 |
| maximum 3 mois après notification |  |  |
| Signature du contrat de jumelage: | m+5 | Mercredi 10 décembre 2025 |
| maximum 3 mois après notification |  |  |
| Démarrage des activités du projet de jumelage: Au plus tard | M+6 | Lundi 19 janvier 2026 |
| 24 mois |  |  |
| Date de fin du projet: | M+14 | Vendredi 18 septembre 2026 |

As per standard grants rules, during the time between the publication and the deadline, Member States should be able to ask questions. The answers provided on points that may be of interest to other Member States should be shared with all of them (see PRAG 6.5.4).