## Slide 1: Implementation, Reporting & Payments
eGrant onboarding for Twinning with lump sum budget
National Contact Points meeting
Berlin, 17 September 2025

## Slide 2: Implementation (1)
Key features of Twinning preserved:
  Twinning standard: Steering committee meetings & rolling work plan
  Twinning light: Steering committee meetings & work plan
No more quarterly interim reports
Monitoring ensured via steering committee meetings & deliverables
  Twinning standard: Quarterly approved rolling work plan at steering committee meetings
  Twinning light: Steering committee meetings and final report including work plan

## Slide 3: Implementation (2)
Changes to activities are reflected in rolling workplan

## Slide 4: Implementation (3)
Financial management
Once the lump sum is fixed in the grant agreement, the costs actually incurred are not reported on
Grant beneficiary can use the budget as they see fit if the project is implemented as agreed.

## Slide 5: Implementation (4)
No contingency reserve

## Slide 6: Implementation (5)
Financial management
Budget changes reflected in the grant agreement require an amendment.

## Slide 7: Implementation (6)
Financial management
Once the lump sum is fixed in the grant agreement, the costs actually incurred are not reported on
Grant beneficiary can use the budget as they see fit if the project is implemented as agreed.
Budget changes reflected in the grant agreement require an amendment.
Notes: Summary slide.

## Slide 8: Reporting
New approach: report on changes
Reporting linked to further pre-financing and final payment
  New template: Periodic report
No more quarterly interim reports
No more reporting on incurred costs
No more expenditure verification report

## Slide 9: Reporting (2)
Periodic report
Periodic report submitted with request for further pre-financing and final payment
Mirrors information sections in the application
Reporting only on changes, except providing summary for section 1.1 work performed and 1.7 communication and visibility

## Slide 10: Reporting (3)
Periodic report:
Reporting on changes
Annexes:
  Work plan
  Logical framework
  Strategic communications plan
  Financial statement (only for final payment

## Slide 11: Reporting (4)
Financial statement
Partially completed work packages are calculated  using detailed budget as a reference point to calculate the changes per activity

## Slide 12: Reporting
Less focus on financial reporting, reduced narrative reporting and more focus on the project content and outputs (currently mandatory results)

## Slide 13: Payment
Payment is not linked with successful outputs (currently mandatory results), but on the completion of work packages (i.e. activities)
Not linked to actual incurred costs

## Slide 14: Payment (2)
Request for further prefinancing
Periodic report
  Annexes:
  Latest approved rolling work plan
  Logical framework
  Strategic Communications plan
Approval by the contracting authority, after consultation of partner country administration
No financial report and reduced narrative reporting
Request for final payment
Periodic report
  Annexes
  Latest approved rolling work plan
  Logical framework
  Strategic Communications plan
  + Financial statement
Approval by the contracting authority, after consultation of partner country administration
No expenditure verification report

## Slide 15: Payment (3)
Prefinancing:
Twinning standard and light: up to 90% prefinancing
Possible configurations for Twinning standard tested:
  Example 1: 40% initial, 50% further prefinancing
  Example 2: 60% initial, 30% further prefinancing
Balance between keeping enough float and minimising risk of recovery

## Slide 16: Thank you
© European Union 2025
Unless otherwise noted the reuse of this presentation is authorised under the CC BY 4.0 license. For any use or reproduction of elements that are not owned by the EU, permission may need to be sought directly from the respective right holders.
Fill in copyright information.