Phase II du Programme d’appui à la réforme de la justice

« NDICI-GEO-NEAR/2022/ACT 61201 »

Jumelage standard

Renforcement des capacités de l’Institut Supérieur de la Magistrature à contribuer à l’amélioration de l’efficacité du système judiciaire

Calendrier de lancement et de mise en œuvre (INDICATIF)

| Action délai | Mois | Date |
| --- | --- | --- |
| Finalisation fiche : | 0 | 08/07/2025 |
| Lancement de l’appel à propositions: | M+1 | Vendredi 10 octobre 2025 |
| minimum 8 semaines |  |  |
| Information day + vc |  | Semaine du 03 novembre 2025 |
| Q&A à publier le cas échéant |  | Avant le 21 novembre 2025 |
| Réception des propositions : | M+3 | Vendredi 05 décembre 2025 |
| Réunions de sélection : |  | Vendredi 19 décembre 2025 |
| idéalement 2 semaines exceptionnellement jusque 4 semaines |  |  |
| Notification des Etats membres : | m+4 | Jeudi 15 janvier 2026 |
| 1 semaine maxi |  |  |
| Confirmation Etat membre sélectionné : |  | Lundi 26 janvier 2026 |
| maximum 3 mois après notification |  |  |
| Signature du contrat de jumelage: | m+7 | Lundi 23 mars 2026 |
| maximum 3 mois après notification |  |  |
| Démarrage des activités du projet de jumelage: Au plus tard |  | Lundi 20 avril 2026 |
| 24 mois |  |  |
| Date de fin du projet: |  | Jeudi 20 avril 2028 |

As per standard grants rules, during the time between the publication and the deadline, Member States should be able to ask questions. The answers provided on points that may be of interest to other Member States should be shared with all of them (see PRAG 6.5.4).