Annex C1a: Simplified logical framework Project title: Support for the strengthening and adaptation of forestry training provision in Côte d’Ivoire Beneficiary administrations: - National School of Water and Forests (ENEF) under the supervision of the Ministry in charge of Water and Forests (MINEF) - Institut National Polytechnique Houphouët-Boigny (INP-HB), under the supervision of the Ministry of Higher Education and Scientific Research (MESRS) Twinning reference: CI 24 NDICI EN 01 25 Publication notice reference: 186706

Project funded by the European Union TWINNING TOOL

Annex C1a: Simplified logical framework

|  | Description | Indicators (with Reference Level and relevant target data) | Sources of verification | Risks | Assumptions (factors external to the project) |
| --- | --- | --- | --- | --- | --- |
| Overall objective | Contribute to strengthening the sustainable and inclusive management of Côte d’Ivoire’s forestry resources | Number of people (disaggregated by type, sex and age) who have benefited from EU-supported vocational education and training (VET) and skills development (initial and continuing training) interventions [Indicator 2.14 GERF] - NR (2025): 0 - Target (end of project): XX (to be defined by the tenderers) | Twinning Implementation Reports |  |  |
| Specific objective (of the project) | Strengthening and adapting forestry training provision in Côte d’Ivoire | Level of validation by the competent authorities of the curricula and training manual renewed and developed - NR (2025): 0 Target (end of project): The curricula and training manuals are ready to: (i) be validated by the competent authorities and (ii) be included in the training offer | Administrative act of validation and/or application prepared | Validation process ready to be initiated | Favourable factor: Good EU relations with MINEF (to be developed with MESRS) |
| Outputs/ mandatory outputs by component | R1: The capacity of the teaching staff to be assessed and strengthened | - Number of persons in ENEF and INP-HB (ESA and EFSPC) whose capacities have been assessed (disaggregation by type, sex and age) - NR (2025): 0 - Target (end of project): 100 - (20 ENEF / 80 INP-HB) - Number of persons in ENEF and INP-HB (ESA and EFSPC) whose capacities have been strengthened (disaggregation by type, sex and age) - NR (2025): 0 Target (end of project): 100 (20 ENEF / 80 INP-HB) | Twinning Implementation Reports Twinning Implementation Reports | Lack of interest and/or availability of teaching staff | Favourable factor: good level of interest and motivation of the teaching staff when preparing this Twinning Fiche |
|  | R2: Renewed initial training curricula are ready to be validated | Number of graduate initial training curricula (from ENEF and INP-HB - ESA) that have been renewed - NR (2025): 0 - Target (end of project): 4 | Pedagogical models shared by ENEF (2) and INP-HB (ESA) (2) | Difference of assessment between the European and Ivorian Schools (including between them) as regards the content of the models to be renewed The possible future new Minister for Water and Forests no longer makes the renewal of the training offer one of his priorities | Favourable factor: some of the EU forestry schools (in France) are already collaborating with some Ivorian schools Favourable factor: the recent creation of ENEF demonstrates a strong desire to integrate forestry education into MINEF |
|  | R3: Renewed continuing education curricula are ready to be validated | Number of graduate continuing education curricula (at ENEF and INP-HB - EFSPC) that have been renewed - NR (2025): 0 - Target (end of project): 3 | Pedagogical models shared by ENEF (1) and INP-HB (EFSPC) (2) |  |  |
|  | R4: Qualifying continuing education offer is developed within INP-HB (ESA) and ENEF | Number of all-public qualifying continuing education manuals (provided to INP-HB – ESA and ENEF) that have been developed - NR (2025): 0 - Target (end of project): 2 | Training manual shared by INP-HB (ESA) and ENEF (2) | Geographical distance from INP-HB and ENEF (based in Yamoussoukro now or in the future) affecting collaboration with the Abidjan-based CRJ Lack of interest from target audiences beyond the forest-wood sector | ‘Favourable’ factor: the majority of INP-HB teachers reside in Abidjan Favourable factor: to varying degrees, Côte d’Ivoire’s agricultural sectors are engaged in agro-forestry activities or zero deforestation |

GENERAL OBJECTIVE: indicate the overall policy objective that goes beyond the immediate scope of the project, but to which the project can contribute. The general objective should be related to the overall sector reform in the beneficiary country, as agreed in the framework of the definition of cooperation with the EU.

These are the changes that will be brought about by the interventions of all project actors and stakeholders at the level of the global political, social, economic and environmental context. These changes require the involvement of third parties that were not direct beneficiaries of the intervention. They are therefore indirectly influenced by EU intervention.

SPECIFIC OBJECTIVE(S) OF THE PROJECT: define the specific objective(s) that will be achieved through the implementation of the Twinning project. These are the effects of the project on the policy, social, economic and environmental areas targeted by the EU intervention as well as changes in the behaviour of the beneficiaries of the EU intervention.

RESULTS / OBLIGATORY PRODUCTS: describe each outcome that the project is expected to achieve, as described in the Twinning Fiche. Each mandatory output/output must correspond to a "project component". Please use one line per pane.

INDICATORS: (with baseline and relevant target data): give an indication of how the achievement of each component of the mandatory results (sub-results by component, results (specific objectives) and impact (general objective)) will be measured. Ensure that the indicators define the following, where appropriate: 1. Measure value (quantity or quality); 2. Baseline and target (values and deadlines); 3. Actors responsible for data collection and reporting; 4. Target group; 5. Deadlines for reporting; 6. Place. The baseline and target data, as indicated in the Twinning Fiche, will be indicated in square brackets next to each indicator. Indicators may be revised if deemed appropriate when developing the initial work plan.

VERIFICATION SOURCES:  for each component, specify the sources of information to prove that the targets have been met: e.g. independent reports, investigations, the Official Journal, Commission reports, etc.

RISKS:  mention the external factors that may hinder the proper implementation of the project, including any events beyond the control of the main actors.

HYPOTHESES:  specify the external conditions and/or initiatives of third parties that may influence the implementation of the project to the extent that only their success can ensure the success of the project. These are the necessary and positive conditions for establishing a proven causal link between the different levels of outcomes.

The French version prevails.